## Capital Projects
7 E. Redwood Street
6 Year Capital Projection (non-leasing)
|  |  | 2023/2024 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10
|  |  | Current Year | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032
|  |  | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Budget | Description/Comments
Roof
| Install new roof anchors per OSHA requirements(Upper Roof) |  |  | Year 2 2024: 50000 | OSHA 1910.27; OSHA 1910.66; IWCA-I 14.1 and ASME120
| Installation of New Roof |  |  | Year 2 2024: 300000 | Estimate to replace both upper and lower roof due to its age and condition
Sturctural Repairs to Building Ceilings | bar: Year 2 2024
HVAC System
| Refurbish air Handlers-services induction/coil units |  |  | Year 3 2025: 10000; Year 4 2026: 10000 | Refurbish with new dampers, actuators; motors; pan coats; insulation of the units - 5 total
| Replace Heat Pumps per floor |  | 55000 | Year 2 2024: 55000; Year 3 2025: 105000; Year 4 2026: 140000; Year 5 2027: 140000; Year 6 2028: 140000 | Replacement of older units located on floors 2,3,5,6,7,9,10,11,14,15,16,17,and 20. All units are manufactured early 1990’s
| Insulate and Replacement of several pumps |  |  | Year 3 2025: 50000; Year 4 2026: 50000 | Remove asbestos and old insulation from piping with new.
| Opterra - VRF System |  |  | Year 5 2027: 1800000; Year 6 2028: 1800000
Electrical System
Switchgear Replacement: | bar: Year 3 2025
|  | Engineering & Design |  | Year 2 2024: 150000 | Consulting fees to Spears/Votta, who researched and developed a replacement plan
|  | Project Costs (Estimate) (2019) |  | Year 2 2024: 2000000; Year 3 2025: 3000000 | Estimated cost of replacement
|  | Replacement Floor Electric Power-Penthouse Elevator |  | Year 3 2025: 1600000 | Cost for future replacement of floor circuit panel boards, to relocate them from stairwell A
| Retrofit of Electrical Panels |  |  | Year 4 2026: 60000; Year 5 2027: 60000 | The existing panels are obsolete, making repairs difficult, new updated panels will be installed which will provide energy efficient and better able to supply adequate electric usage to each floor without tripping breakers.
| HVAC Continuous Work - (JCI) |  |  | Year 2 2024: 200000 | To connect all heat pumps & AHU to building system for control ($10,000 per floor)
Plumbing System
| Replacement of Pumps |  |  | Year 2 2024: 30000; Year 3 2025: 30000 | We will need to rebuild or replace the following pumps: 3 sump pumps; 1 chill water pump; 1 standby pump used for the chilled/condenser loop; domestic water pumps
| Coating of interior pipes- condensor & chilled water lines that are located in shaft. |  |  | Year 3 2025: 800000 | Condensor & Chilled Water Lines
Elevators
| Consultant |  | 48500 | [9 empty] | Consulting fee to determine the course of action for the replacement/upgrade of elevators
| Car Safety Upgrade Elevator #1 | [11 empty] | Car safety device is obsolete.
| Motor Control Upgrade |  |  | Year 2 2024: 175328; Year 3 2025: 175328 | $43,832 per elevator. Current motor control is obselete.
| Modernization |  |  | Year 2 2024: 3000000; Year 5 2027: 500000 | this estimate was provided by Otis Elevator 2015
| Card Readers |  |  | Year 3 2025: 75000 | 7 Elevators - 7 points of access
Life Safety Systems
| Fire Alarm Panel Replacement |  |  | Year 4 2026: 800000 | Current panel is obsolete making repairs difficult and causing excessive service calls - also Fire Marshals are requesting that the building be brought to code and a speaker system be installed throughout the building.
Security Systems
Common Areas - Interior
| Lead Abatement (Stairwell) |  | 45000 | Year 2 2024: 45000 | Stairwells A & B - Basement through Penthouse. Quote received for $18K for 4 floors. | Added 2022
| Lead Abatement (Penthouse; Trash Room & Basement) |  |  | Year 3 2025: 200000 | $75K for Penthouse Area after the domestic tanks have been removed; $50K - Trash Room; $75K for basement
Building/ Structure
| Façade Consulting |  | 40000 | [9 empty] | Façade consulting | Budgeting $2000 per week ($8666 p/m) for Building Envelope Consultants consulting for June 2023 and $250 payable to Structural for remaining contract amount.
| Exterior Façade Caulking & Waterproofing |  | 300000 | [9 empty] | Building façade project in progress. | $1,810,266 for Redwood & Light St and $667,734 for Lovegrove & Mercer (alleys). $250,000 for a continency. $250K placeholderfor FY 23-24 budget
| Refurbishment of Metal Bars at street level |  |  | Year 4 2026: 300000
| Building Antennas | [11 empty] | Removal of the mickey mouse on the second roof
| Branch Windows |  | 75000 | [9 empty] | Some of the windows at the street level are cracked and need to be replaced
TOTAL BUILDING IMPROVEMENTS & EQUIPMENT |  |  | 563500 | Year 2 2024: 6005328; Year 3 2025: 6045328; Year 4 2026: 1360000; Year 5 2027: 2500000; Year 6 2028: 1940000
Note on B25: Karen Curry/USA: this item has been proposed for the past year and has not been approved.
Note on D41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: BECS remaining fees.
Note on D42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Due to Structural for remaining project.